## Pre-Phase — People
✓ | Task | Owner | Timeline | Notes
VISION & ALIGNMENT
☐ | Write or adopt your community manifesto/vision document | Founding household | Month 1 | Use SMF Manifesto as template
☐ | Define your three core values and non-negotiables | Founding household | Month 1 | SMF: Children's safety, Be who you are, Don't harm
☐ | Decide on governance model (council, consensus, hybrid) | Founding group | Month 1-2 | SMF recommends council of households
☐ | Establish the matriarchal framework: who is vulnerable, what protects them | Founding group | Month 1-2 | Blueprint Section 7
☐ | Set initial household buy-in amount and financial model | Founding group | Month 2 | SMF default: $12,500/household
☐ | Decide CLT vs other legal structure | Founding group + attorney | Month 2-3 | SMF recommends 501(c)(2) CLT
RECRUITMENT — FINDING YOUR 12
☐ | Write your community description/recruitment posting | Founding household | Month 2 | See Recruitment Guide
☐ | Post in intentional community networks (IC.org, FIC, local groups) | Designated recruiter | Month 2-3
☐ | Post in aligned communities (permaculture, homesteading, unschooling) | Designated recruiter | Month 2-3
☐ | Develop screening conversation guide | Founding group | Month 2 | See Recruitment Guide
☐ | Conduct initial screening conversations (phone/video) | Founding group | Ongoing | Document each conversation
☐ | Schedule and host trial visits (3-7 days minimum) | Founding group | Month 3-8 | See Recruitment Guide for structure
☐ | Conduct mutual assessment after each trial visit | Both parties | After each visit | Both sides decide — it's mutual
☐ | Run background checks on all prospective adult members | Designated member | Before commitment | Criminal, sex offender, child abuse registry
☐ | Present full covenant, safeguarding policies, and Hard Truths | Founding group | Before commitment | No surprises — full transparency
☐ | Collect signed membership agreements from committed households | Financial manager | Before buy-in
☐ | Reach minimum viable group (4-6 households to start) | All | Month 6-12 | Don't rush — wrong people cost more than waiting
FINANCIAL PREPARATION
☐ | Open community bank account (requires LLC or CLT formation) | Financial manager | Month 3 | Dual-signature required
☐ | Collect buy-in commitments (written, not yet deposited) | Financial manager | Month 4-6
☐ | Develop detailed operating budget using SMF Financial Model | Financial manager | Month 3-4 | Customize for your region
☐ | Research land prices in target region(s) | Land search team | Month 2-6 | Use SMF Town Evaluation tool
☐ | Identify funding sources beyond buy-ins (grants, loans, donors) | Financial manager | Month 3-6 | USDA loans, conservation easements, impact investors
☐ | Retain accountant familiar with nonprofit agriculture | Financial manager | Month 4 | See Vendor Directory
LEGAL FORMATION
☐ | Retain attorney experienced in CLTs or land trusts | Founding household | Month 3 | Critical hire — do not skip
☐ | File articles of incorporation for CLT (501(c)(2) or state equivalent) | Attorney | Month 4-5
☐ | Draft and adopt CLT bylaws | Attorney + founding group | Month 4-5 | Use template as starting point
☐ | Draft ground lease template | Attorney | Month 5-6
☐ | Apply for 501(c)(2) tax-exempt status (if applicable) | Attorney | Month 5-6 | Can take 6-12 months
☐ | Draft household membership agreement | Attorney + founding group | Month 5 | Include all covenant-level commitments
☐ | Obtain EIN from IRS | Financial manager | Month 4 | Required for bank account

## Phase 1 — Land
✓ | Task | Owner | Timeline | Notes
LAND SEARCH
☐ | Define land criteria (acreage, water, soil, zoning, distance to services) | Land search team | Week 1-2 | Use SMF Town Evaluation tool
☐ | Research target counties/regions | Land search team | Week 1-4 | Climate, politics, cost of living, hospital proximity
☐ | Contact rural real estate agents in target areas | Land search team | Week 2-4 | Tell them CLT — some won't understand
☐ | Visit top 3-5 candidate properties | Land search team + at least 2 households | Week 4-12 | Bring soil probe, water test kit, camera
☐ | Verify zoning allows multi-household residential + agriculture | Attorney | Before offer | Critical — some counties prohibit this
☐ | Test water source(s) — well yield, spring flow, water quality | Professional tester | Before offer | Budget: $500-$1,500
☐ | Soil test (percolation for septic, fertility for farming) | County extension / professional | Before offer | Budget: $200-$500
☐ | Survey property boundaries | Licensed surveyor | Before closing | Budget: $1,000-$3,000
☐ | Title search and title insurance | Title company | Before closing
☐ | Environmental assessment (optional but recommended) | Environmental consultant | Before closing | Check for contamination, wetlands, flood zones
PURCHASE & LEGAL
☐ | Collect buy-in deposits into CLT account | Financial manager | Before closing | $12,500 x committed households
☐ | Make offer and negotiate purchase | Designated negotiator + attorney | Week 8-16
☐ | Secure financing if needed (USDA, conservation lender, private) | Financial manager | Week 8-16
☐ | Close on property — title transfers to CLT | Attorney + financial manager | Closing day | CLT holds title, not individuals
☐ | Execute ground leases for each committed household | Attorney | At or after closing
☐ | Record deed and ground leases with county | Attorney | After closing
INSURANCE (BEFORE ANYONE MOVES ON)
☐ | Obtain general liability insurance for CLT | Financial manager | Before move-in | $1M/$2M minimum
☐ | Obtain farm liability / agritourism rider | Financial manager | Before operations | Required if CSA or visitors
☐ | Obtain umbrella policy ($1-2M) | Financial manager | Before move-in | Protects CLT from catastrophic claims
☐ | Confirm each household has renters/homeowners insurance | Each household | Before move-in | Individual responsibility
☐ | Obtain builders risk insurance (if constructing) | Financial manager | Before construction
SAFETY SETUP
☐ | Identify nearest hospital, ER, trauma center, urgent care | Designated member | Before move-in | Post directions in every dwelling
☐ | Identify nearest OB-GYN, midwife, pediatrician | Designated member | Before move-in
☐ | Establish relationship with nearest DV shelter and hotline | Designated safe contact | Before move-in | Post number in common areas
☐ | Post emergency contacts and 911 GPS coordinates | Farm manager | Before move-in | Every dwelling + common house
☐ | Install cameras in shared outdoor spaces | Infrastructure team | First month | Community-owned system
☐ | Set up first aid station in common area | Health lead | Before move-in | AED, full supplies per Blueprint 8.4
☐ | Retain external ombudsperson | Council | First 90 days | Licensed professional, no community ties

## Phase 2 — Infrastructure
✓ | Task | Owner | Timeline | Notes
WATER
☐ | Drill or develop well(s) — minimum 5 GPM for 12 households | Licensed well driller | Week 1-4 | Budget: $5,000-$15,000
☐ | Install water storage (cistern, tank) — minimum 5,000 gal | Plumber / contractor | Week 2-6
☐ | Install water distribution system to household sites | Plumber | Week 4-8
☐ | Water quality test and filtration if needed | Testing lab | After well completion | Test annually
☐ | Plan irrigation system for gardens and livestock | Farm manager | Week 4-8 | Drip preferred for conservation
SEPTIC & WASTE
☐ | Percolation test for septic siting | Septic engineer | Week 1-2 | County may require specific sites
☐ | Install septic system(s) — permits required | Licensed installer | Week 4-12 | Budget: $10,000-$30,000
☐ | Plan composting system (humanure, kitchen, farm waste) | Farm manager | Week 4-8 | Vermicomposting recommended
☐ | Set up recycling and waste management | Operations lead | Week 2-4
POWER
☐ | Assess solar potential (orientation, shading, roof space) | Solar installer | Week 1-4
☐ | Install solar array + battery storage (if off-grid) | Licensed electrician | Week 4-12
☐ | Connect to grid or install backup generator | Electrician | Week 4-8
☐ | Distribute power to household sites | Electrician | Week 6-12
HOUSING
☐ | Grade and prepare household sites per community layout | Excavator | Week 2-6 | See Community Layout plan
☐ | Install temporary housing for first arrivals (RV pads, yurts, tiny homes) | First households | Week 1-4
☐ | Begin permanent dwelling construction (phased by household) | Each household + community | Month 2-12+ | Work parties for communal builds
☐ | Build or designate common house | Community | Month 3-6 | ADA accessible — wheelchair, sensory spaces
☐ | Ensure all common buildings meet accessibility standards | Infrastructure lead | Ongoing | See Blueprint 7.9
ROADS & ACCESS
☐ | Grade internal roads/paths to all household sites | Excavator | Week 2-6
☐ | Ensure emergency vehicle access to all dwellings | Infrastructure lead | Before occupancy | Fire truck turning radius
☐ | Install accessible pathways between common areas | Infrastructure lead | Month 2-4 | Graded gravel or paved — mobility devices
FENCING & SECURITY
☐ | Install perimeter fencing (livestock containment + predator deterrent) | Fencing crew | Month 1-3
☐ | Install garden fencing (deer, rabbit) | Garden team | Before planting
☐ | Install property entrance gate and camera | Infrastructure lead | Month 1-2

## Phase 3 — Growing
✓ | Task | Owner | Timeline | Notes
SOIL & GARDENS
☐ | Comprehensive soil test — nutrients, pH, organic matter, contaminants | County extension | Before planting | Baseline for regenerative plan
☐ | Amend soil based on test results (compost, lime, minerals) | Garden team | 4-6 weeks before planting | Organic/regenerative inputs only
☐ | Establish compost system (3-bin minimum, vermicomposting) | Farm manager | Month 1
☐ | Plant cover crops on all non-active beds | Garden team | Immediately | Clover, vetch, rye — soil building
☐ | Build raised beds and/or prepare in-ground plots | Garden team | Month 1-2
☐ | Plan and plant first-season crops (focus on reliable producers) | Farm manager | Season-dependent | Start conservative — tomatoes, greens, squash, beans
☐ | Establish herb garden (culinary + medicinal) | Designated member | Month 1-2 | Joe Hollis / Mountain Gardens inspiration
☐ | Plant perennial food systems (fruit trees, berry bushes, asparagus) | Farm manager | Year 1 | Long-term investment — won't produce immediately
☐ | Begin seed saving program | Designated member | First harvest | Open-pollinated varieties only
LIVESTOCK
☐ | Build chicken coop and run (start with layers) | Animal team | Month 1-2 | 12-24 hens for 12 households
☐ | Acquire first flock | Farm manager | After coop ready | Heritage breeds recommended
☐ | Build goat shelter and fencing (if planned) | Animal team | Month 2-4
☐ | Establish animal care rotation and training | Farm manager | Before animals arrive | See Blueprint 8.5 — safety certs for large animals
☐ | Set up veterinary relationship | Farm manager | Before animals arrive | Large animal vet — may be far in rural areas
CSA & INCOME
☐ | Research local CSA market and pricing | CSA coordinator | Month 1-3
☐ | Develop CSA membership structure and pricing | CSA coordinator + financial manager | Month 2-4
☐ | Register with state for cottage food / farm sales (if required) | CSA coordinator | Before first sale | State-specific laws
☐ | Begin farmers market presence (if applicable) | CSA coordinator | When harvest allows
☐ | Plan value-added products (preserves, soap, herbs) | Designated members | Year 1-2 | Additional income streams
CERTIFICATIONS
☐ | Begin USDA Organic transition (3-year process) | Farm manager | Year 1 | Document everything from day one
☐ | Research Regenerative Organic Certified (ROC) pathway | Farm manager | Year 1 | Requires organic certification first
☐ | Maintain detailed farm records (inputs, practices, yields) | Farm manager | Ongoing | Required for certification

## First 90 Days
Week | Priority | Task | Owner | Depends On | Done
WEEK 1
Week 1 | CRITICAL | Secure water source — test well, verify flow rate | Infrastructure lead | Land closed | ☐
Week 1 | CRITICAL | Post emergency contacts + hospital directions in all dwellings | Farm manager |  | ☐
Week 1 | CRITICAL | Install temporary housing for first households | First arrivals | Sites identified | ☐
Week 1 | HIGH | Hold founding governance meeting — elect interim council roles | All households present |  | ☐
Week 1 | HIGH | Set up communication system (group text, radio, shared calendar) | Operations lead |  | ☐
Week 1 | HIGH | Install cameras at property entrance and common areas | Infrastructure lead | Power available | ☐
Week 1 | MEDIUM | Walk entire property — document existing features, hazards, assets | All |  | ☐
Week 1 | MEDIUM | Introduce yourselves to nearest neighbors | Founding household |  | ☐
WEEK 2
Week 2 | CRITICAL | Begin well drilling or water system development | Licensed driller | Permits obtained | ☐
Week 2 | HIGH | Establish first aid station in common area or largest dwelling | Health lead | Supplies purchased | ☐
Week 2 | HIGH | Set up community bank account if not already done | Financial manager | EIN obtained | ☐
Week 2 | HIGH | Begin percolation testing for septic | Septic engineer |  | ☐
Week 2 | MEDIUM | Begin clearing and grading household sites | Infrastructure team | Layout agreed | ☐
Week 2 | MEDIUM | Start composting operation | Farm manager |  | ☐
Week 2 | MEDIUM | Begin soil testing | Farm manager |  | ☐
WEEK 3
Week 3 | HIGH | First community meal — establish the culture from day one | Rotating household |  | ☐
Week 3 | HIGH | Distribute onboarding packets to all households | Council | Packets prepared | ☐
Week 3 | HIGH | Complete mandatory reporter training for all adults | All adults | Training scheduled | ☐
Week 3 | MEDIUM | Begin garden bed preparation | Garden team | Soil tests back | ☐
Week 3 | MEDIUM | Install temporary fencing for first livestock area | Animal team | Posts + wire | ☐
Week 3 | MEDIUM | Schedule CPR/First Aid certification for all households | Health lead |  | ☐
WEEK 4
Week 4 | HIGH | First formal governance meeting with full agenda | Council | Agenda distributed 7 days prior | ☐
Week 4 | HIGH | Establish farm duty rotation (even with partial households) | Farm manager |  | ☐
Week 4 | HIGH | Begin background checks on any adults not yet cleared | Designated member |  | ☐
Week 4 | MEDIUM | First New Moon dinner | Rotating household |  | ☐
Week 4 | MEDIUM | Begin electrical/solar installation | Electrician | Permits | ☐
Week 4 | MEDIUM | Plant cover crops on all non-active land | Garden team |  | ☐
WEEK 5-6
Week 5-6 | HIGH | Complete water system installation and testing | Plumber | Well done | ☐
Week 5-6 | HIGH | Begin septic installation | Licensed installer | Permits + perc test | ☐
Week 5-6 | HIGH | First Full Moon dinner | Rotating household |  | ☐
Week 5-6 | HIGH | All adults complete CPR/First Aid certification | All |  | ☐
Week 5-6 | MEDIUM | Begin permanent common house construction or designation | Community |  | ☐
Week 5-6 | MEDIUM | First skill share | Volunteer household |  | ☐
Week 5-6 | MEDIUM | Establish veterinary relationship | Farm manager |  | ☐
WEEK 7-8
Week 7-8 | HIGH | Establish relationship with external ombudsperson | Council | Candidates identified | ☐
Week 7-8 | HIGH | Retain insurance broker — obtain all required policies | Financial manager |  | ☐
Week 7-8 | HIGH | First quarterly financial report to full community | Financial manager |  | ☐
Week 7-8 | MEDIUM | First livestock arrives (chickens recommended first) | Farm manager | Coop + run built | ☐
Week 7-8 | MEDIUM | Begin accessible pathway construction | Infrastructure team |  | ☐
Week 7-8 | MEDIUM | Post DV shelter and hotline information in common areas | Safe contact |  | ☐
WEEK 9-10
Week 9-10 | HIGH | All households complete firearms storage compliance (if applicable) | Farm manager | Policy distributed | ☐
Week 9-10 | HIGH | All households complete safety certifications for equipment they operate | Farm manager |  | ☐
Week 9-10 | HIGH | Establish children's safe adult program | Council + children | See Blueprint 7.6.7 | ☐
Week 9-10 | MEDIUM | First work party — community build project | Farm manager |  | ☐
Week 9-10 | MEDIUM | Begin CSA research and market assessment | CSA coordinator |  | ☐
Week 9-10 | MEDIUM | Plan holiday calendar for remainder of year | Council |  | ☐
WEEK 11-12
Week 11-12 | HIGH | First quarterly governance review — what's working, what's not | Council + ombudsperson |  | ☐
Week 11-12 | HIGH | Complete onboarding for any households that arrived after week 1 | Council |  | ☐
Week 11-12 | HIGH | Verify all insurance policies are in place and adequate | Financial manager |  | ☐
Week 11-12 | MEDIUM | First harvest celebration (even if small) | All |  | ☐
Week 11-12 | MEDIUM | Begin planning for next wave of households (if not at 12) | Recruitment lead |  | ☐
Week 11-12 | MEDIUM | Document all operational knowledge in shared manual | All role holders | See Farm Ops Manual | ☐
WEEK 13
Week 13 | HIGH | MILESTONE: 90-day community assessment | Council + ombudsperson |  | ☐
Week 13 | HIGH | Review and adjust financial model based on actual costs | Financial manager |  | ☐
Week 13 | HIGH | Review and adjust duty rotation based on actual capacity | Farm manager |  | ☐
Week 13 | MEDIUM | Celebrate making it 90 days — this is real now | Everyone |  | ☐

## State Legal Checklist
Category | Item | Your State Requirement | Status | Notes
Land & Zoning
| Agricultural zoning — does your parcel allow multi-household residential? |  | ☐
| Minimum lot size per dwelling unit |  | ☐
| Setback requirements from property lines |  | ☐
| Maximum number of dwellings per parcel |  | ☐
| ADU (accessory dwelling unit) regulations |  | ☐
| RV/tiny home/yurt regulations for temporary or permanent housing |  | ☐
| Building permit requirements and process |  | ☐
| Septic system permit requirements |  | ☐
| Well drilling permit requirements |  | ☐
Water Rights
| Water rights doctrine (prior appropriation vs riparian) |  | ☐
| Well drilling permit and registration |  | ☐
| Maximum well depth and yield restrictions |  | ☐
| Rainwater harvesting legality and restrictions |  | ☐
| Greywater reuse regulations |  | ☐
| Surface water use rights (creek, spring, pond) |  | ☐
CLT & Nonprofit
| State nonprofit incorporation requirements |  | ☐
| CLT-specific legislation (if any) |  | ☐
| Property tax treatment of CLT-held land |  | ☐
| Ground lease recording requirements |  | ☐
| State attorney general nonprofit oversight requirements |  | ☐
| Annual reporting requirements for nonprofits |  | ☐
Agriculture
| Right to farm laws (protection from nuisance complaints) |  | ☐
| USDA Organic certification — state organic program (SOP) or NOP direct |  | ☐
| Cottage food laws — what can you sell without a commercial kitchen? |  | ☐
| Raw milk sale legality (legal, herdshare only, or prohibited) |  | ☐
| Farmers market vendor permit requirements |  | ☐
| Livestock regulations — permitted species, density limits |  | ☐
| Slaughter regulations (on-farm, custom exempt, USDA inspected) |  | ☐
| Composting regulations (humanure, animal waste) |  | ☐
Education
| Homeschool notification requirements |  | ☐
| Homeschool curriculum requirements (if any) |  | ☐
| Homeschool assessment/testing requirements |  | ☐
| Co-op teaching regulations — do co-op teachers need credentials? |  | ☐
| Compulsory attendance ages |  | ☐
Firearms
| State safe storage laws (if any) |  | ☐
| Concealed carry permit requirements |  | ☐
| State preemption of local firearms regulations |  | ☐
| Minimum age for firearm possession |  | ☐
| Restrictions on specific firearm types |  | ☐
Child Safety & Family
| Mandatory reporter requirements by profession |  | ☐
| Background check process for child abuse registry |  | ☐
| Sex offender registry access and restrictions |  | ☐
| Child protective services — reporting process and response times |  | ☐
| Home-based childcare regulations (if childcare rotation is formalized) |  | ☐
Insurance & Liability
| State minimum liability insurance requirements for farm operations |  | ☐
| Agritourism liability protections (some states have liability shields) |  | ☐
| Volunteer liability protections |  | ☐
| Attractive nuisance doctrine application (ponds, equipment, structures) |  | ☐

## Vendor Directory
Category | Role / Service | Company / Name | Contact | Phone | Status | Notes
Legal
| CLT / Land Trust Attorney |  |  |  | ☐ Not Started
| General Business Attorney |  |  |  | ☐ Not Started
| Real Estate Attorney |  |  |  | ☐ Not Started
| Tax Attorney (nonprofit) |  |  |  | ☐ Not Started
| Mediator / Conflict Resolution Professional |  |  |  | ☐ Not Started
Financial
| Accountant (nonprofit agriculture experience) |  |  |  | ☐ Not Started
| Bookkeeper |  |  |  | ☐ Not Started
| Insurance Broker (farm policies) |  |  |  | ☐ Not Started
| Bank / Credit Union (nonprofit accounts) |  |  |  | ☐ Not Started
| Grant Writer |  |  |  | ☐ Not Started
Land & Construction
| Real Estate Agent (rural / agricultural) |  |  |  | ☐ Not Started
| Licensed Surveyor |  |  |  | ☐ Not Started
| Title Company |  |  |  | ☐ Not Started
| Excavation / Grading Contractor |  |  |  | ☐ Not Started
| General Contractor |  |  |  | ☐ Not Started
Infrastructure
| Well Driller |  |  |  | ☐ Not Started
| Plumber |  |  |  | ☐ Not Started
| Licensed Electrician |  |  |  | ☐ Not Started
| Solar Installer |  |  |  | ☐ Not Started
| Septic System Installer |  |  |  | ☐ Not Started
Farm
| Large Animal Veterinarian |  |  |  | ☐ Not Started
| County Extension Agent |  |  |  | ☐ Not Started
| Seed Supplier (organic / open-pollinated) |  |  |  | ☐ Not Started
| Feed Supplier (organic) |  |  |  | ☐ Not Started
| Equipment Dealer / Repair |  |  |  | ☐ Not Started
Health & Safety
| Nearest Hospital / ER |  |  |  | ☐ Not Started
| Nearest Trauma Center |  |  |  | ☐ Not Started
| Nearest Urgent Care |  |  |  | ☐ Not Started
| OB-GYN / Midwife / Birth Center |  |  |  | ☐ Not Started
| Pediatrician |  |  |  | ☐ Not Started
| Perinatal Mental Health Provider |  |  |  | ☐ Not Started
| Trauma-Informed Therapist / Counselor |  |  |  | ☐ Not Started
| Domestic Violence Shelter / Hotline |  |  |  | ☐ Not Started
| Substance Abuse Treatment Center |  |  |  | ☐ Not Started
| CPR / First Aid Training Provider |  |  |  | ☐ Not Started
Governance & Oversight
| External Ombudsperson |  |  |  | ☐ Not Started
| Third-Party Accountant (annual review) |  |  |  | ☐ Not Started
| Firearms Safety Certification Provider |  |  |  | ☐ Not Started
| Mandatory Reporter Training Provider |  |  |  | ☐ Not Started